## Slide 1: VTC Final Management Meeting Sept. 28- Oct. 2, 2018 Leipzig

## Slide 2
WP 1 | Tasks | WP Leader-Coleader | Status
Review, State of the art and Network between partner | 1.1 Project start up activities (due date:30-10-2015) | HTWK - JUST | Done in Feb, 2016
 | 1.2 Prepare operation plans for the skills and guidance sector of the VTC (due date: 1.8.2016) | SUA-UJ- BAU- HTWK- AGORA | Pending

## Slide 3
WP2 :Assessment studies for the needs of students | 2.1 Generic vocational skills and competencies (due date: 2.5.2016) | BAU- AEG- JUST | BAU and AEG prepared surveys on the needed skills and competencies for different disciplines All JO partners prepared reports on skills and competencies needed. JUST finalized the final report
 | 2.2 List of equivalence of vocational skills and of needed skills (due date: 1.6.2016) | JUST, BAU, all JO partners | All JO partners prepared reports on skills and competencies needed. JUST finalized the final report
 | 2.3 Analyze qualifications required by the labour market (due date: 1.7.2016) | JUST, BAU, all JO partners | All JO partners prepared reports on skills and competencies needed. JUST finalized the final report

## Slide 4
WP3: Employment sector database | 3.1 Nominate IT specialists at consortium universities (due date: 1.6.2016) | JUST- All partners should nominate the IT specialist | JUST has hired an ICT specialist. All JO partners need to nominate one ICT specialist to be in their team
 | 3.2 Develop a data base for universities/companies (due date:1.7.2016) | JU, MU | -JUST has prepared some database on universities and companies

## Slide 5
WP 4: Purchase of teaching equipment and bibliographic material | 4.1 Selection of Equipment (due date:1.4.2016 & 1.10.2016 purchasing ) | JUST, GJU | JUST and GJU have prepared a list of suitable equipment JUST obtained 3 offers for purchasing the equipment HTWK approved the supplier for the equipment 25 PCs and server have been installed at all JO Universities
 | 4.2 Implementation of the center (due date:15.6.2017) | GJU-All Jo Partners | All of partners have established the VTC at their universities

## Slide 6
WP 5:Make vocational skill competency development an integrated part in Teaching | 5.1 Develop teaching and learning programs for the VTC (due date:1.12.2016) | ISPAB- P&B- ALL Partners | Completed
 | 5.2 Train lecturers in competency based learning (due date:1.12.2016) | ISPAB- P&B- All Partners | Completed

## Slide 7
WP 6:Career guidance and counseling programs for the career sector | 6.1 Workshops and trainings in career planning and career startup (due date:15.10.2016) | AGORA-SUA All Jo Partners | Completed
 | 6.2 Establish an online career information system (due date:15.6.2016) | AGORA-All Partners | Completed
 | 6.3 Organize an annual job fair ( due date:1.2.2017) | AGORA-All Partners | All JO partners organized info days

## Slide 8
WP 7:Quality control and monitoring | 7.1 Quality control, monitoring and budgetary control ( due date:15.10.2015) | AABU, MU | Completed
 | 7.2 Check of courses materials & courses & vocational systems ( due date:15.7.2016) | HTWK- All Partners | Completed
 | 7.3 Project task supervision, result evaluation and examination of courses results ( due date:15.10.2015) | HTWK- All Partners | Completed

## Slide 9
WP8:DISSEMINATION & EXPLOITATION | 8.1: Opening of the project data base and the VTC for external partners via Internet (due date:15.10.2015) | JU, JUST | Completed
 | 8.2: Prepare and conduct internal/external (due date:15.10.2015) | MU All Jo Partners | Internal completed, External?
 | 8.3: Participation in annual Erasmus project representatives meeting and job fairs (due date 15.7.2017) | HTWK- JUST | Completed
 | 8.4: Distribution of project documentation material ( due date:15.7.2017) | MU-All Partners | Completed

## Slide 10
WP9: Exploitation of results and sustainability | 9.1: Involve the public/private employment sector in activities/services of the VTC (due date:01.03.2018) | AEG-GJU- P&B- JU | Completed
 | 9.2: Establish a training center (regional) in universities as part of the universities (due date:15.03.2018) | GJU and AEG- All Jo Partners | GJU
 | 9.3: Workshop on broader strategic options as follow‐up project activities ( due date:15.3.2018) | BAU- All Jo Partners | Completed

## Slide 11
WP10: Coordination and management of the project | Duration:15.10.2015 to 14.10.2018 | HTWK- JUST | Continuous process

## Slide 12
Thank you