## Slide 1: Vocational training center for undergraduate university students and teachers in Jordan (VTC)
VTC WPs Status for the Monitoring Visit
Presented by:
Prof. Fahmi Abu Al-Rub, JUST
Dr. Riyadh Qashi, HTWK
At the university of Jordan
Amman-jordan
Oct 30, 2016
VTC Project Number: 561708-EPP-1-2015-1-DE-EPPKA2-CBHE-JP

## Slide 2
WP 1 | Tasks | WP Leader-Coleader | Status
Review, State of the art and Network between partner | 1.1 Project start up activities (due date:30-10-2015) | HTWK - JUST | Done in Feb, 2016
 | 1.2 Prepare operation plans for the skills and guidance sector of the VTC (due date: 1.8.2016) | SUA-UJ- BAU- HTWK- AGORA | Pending

## Slide 3
WP2: Assessment studies for the needs of students | 2.1 Generic vocational skills and competencies (due date: 2.5.2016) | BAU- AEG- JUST | BAU and AEG prepared surveys on the needed skills and competencies for different disciplines vtc-cover- survey engineering students.docx All JO partners prepared reports on skills and competencies needed. JUST finalized the final report Local needs- WP2 report.pdf

## Slide 4
WP2: Assessment studies for the needs of students |  |  | 
 | 2.2 List of equivalence of vocational skills and of needed skills (due date: 1.6.2016) | JUST, BAU, all JO partners | All JO partners prepared reports on skills and competencies needed. JUST finalized the final report
 | 2.3 Analyze qualifications required by the labour market (due date: 1.7.2016) | JUST, BAU, all JO partners | All JO partners prepared reports on skills and competencies needed. JUST finalized the final report

## Slide 5
WP3: Employment sector database | 3.1 Nominate IT specialists at consortium universities (due date: 1.6.2016) | JUST- All partners should nominate the IT specialist | JUST has hired an ICT specialist. All JO partners need to nominate one ICT specialist to be in their team
 | 3.2 Develop a data base for universities/companies (due date:1.7.2016) | JU, MU | -JU, BAU and JUST have prepared some database on universities and companies

## Slide 6
WP4: Purchase of teaching equipment and bibliographic material | 4.1 Selection of Equipment (due date:1.4.2016 & 1.10.2016 purchasing ) | JUST, GJU | JUST and GJU have prepared a list of suitable equipment JUST obtained 3 offers for purchasing the equipment HTWK approved the supplier for the equipment 25 PCs and server have been installed at all JO Universities Smart board, interactive data show has been purchased of JUST and BAU
 | 4.2 Implementation of the center (due date:15.6.2017) | GJU-All JO Partners | Most of partners have established the VTC at their universities

## Slide 7
WP5: Make vocational skill competency development an integrated part in Teaching | 5.1 Develop teaching and learning programs for the VTC (due date:1.12.2016) | ISPAB- P&B- ALL Partners | 10 training workshops have been realized and prepared
 | 5.2 Train lecturers in competency based learning (due date:1.12.2016) | ISPAB- P&B- All Partners | Pending

## Slide 8
WP6: Career guidance and counseling programs for the career sector | 6.1 Workshops and trainings in career planning and career startup (due date:15.10.2016) | AGORA-SUA All Jo Partners | Pending
 | 6.2 Establish an online career information system (due date:15.6.2016) | AGORA-All Partners | Pending
 | 6.3 Organize an annual job fair ( due date:1.2.2017) | AGORA-All Partners | JUST has participated in the Job Fair in May 2016 and disseminated VTC project

## Slide 9
WP7: Quality control and monitoring | 7.1 Quality control, monitoring and budgetary control ( due date:15.10.2015) | AABU, MU | AABU has prepared draft of quality and monitoring plans
 | 7.2 Check of courses materials & courses & vocational systems ( due date:15.7.2016) | HTWK- All Partners | Pending
 | 7.3 Project task supervision, result evaluation and examination of courses results ( due date:15.10.2015) | HTWK- All Partners | Pending

## Slide 10
WP8: DISSEMINATION & EXPLOITATION | 8.1: Opening of the project data base and the VTC for external partners via Internet (due date:15.10.2015) | JU, JUST | Has prepared a draft od the dissemination plan
 | 8.2: Prepare and conduct internal/external information events, mid-term/final Conferences (due date:15.10.2015) | MU All Jo Partners | MU will organize an info day and dissemination activity by mid Dec. 2016
 | 8.3: Participation in annual Erasmus project representatives meeting and job fairs (due date 15.7.2017) | HTWK- JUST | JUST has participated in a Job fair at JUST in May 2017
 | 8.4: Distribution of project documentation material ( due date:15.7.2017) | MU-All Partners | Pending

## Slide 11
WP9: Exploitation of results and sustainability | 9.1: Involve the public/private employment sector in activities/services of the VTC (due date:01.03.2018) | AEG-GJU- P&B- JU | Pending
 | 9.2: Establish a training center (regional) in universities as part of the universities (due date:15.03.2018) | BAU- All Jo Partners | BAU has established a regional training center
 | 9.3: Workshop on broader strategic options as follow‐up project activities ( due date:15.3.2018) | BAU- All Jo Partners | Pending

## Slide 12
WP10: Coordination and management of the project | Duration: 15.10.2015 to 14.10.2018 | HTWK- JUST | Continuous process

## Slide 13
Thank you